## GanttChart
[Project Name] Project Schedule
[Company Name]
| Project Start Date | 2018-01-29 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | [7 empty] | 2018-01-29 | [6 empty] | 2018-02-05 | [6 empty] | 2018-02-12 | [6 empty] | 2018-02-19 | [6 empty] | 2018-02-26 | [6 empty] | 2018-03-05 | [6 empty] | 2018-03-12 | [6 empty] | 2018-03-19
 | time axis 2018-01-29 to 2018-03-25
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2018-01-29 to 2018-03-25
1 | Create Project |  |  |  | - |  |  | -
.1 | Create Bitbucket repository | [Name] |  | 2018-11-05 | 2018-11-05 | 1 | 0% | 1
0.2 | Create branches for development, production and testing Environments |  |  | 2018-11-05 | 2018-11-05 | 1 | 0% | 1
0.3 | Create Python project structure |  |  | 2018-11-05 | 2018-11-07 | 2 | 0% | 3
2 | ETL |  |  |  | - |  |  | -
0.1 | Requirement Gathering and task breakdown |  |  | 2018-11-08 | 2018-11-12 | 3
0.2 | Fetch all the response JSON files from Postgres |  |  | 2018-11-13 | 2018-11-13 | 1 | 0% | 1
0.3 | Analyse the folder structure |  |  | 2018-11-09 | 2018-11-09 | 1 | 0% | 1
0.4 | Analyse the JSON files data |  |  | 2018-11-12 | 2018-11-14 | 2 | 0% | 3
0.5 | Find out all the mandatory and optional fields in the JSON files |  |  | 2018-11-15 | 2018-11-16 | 2 | 0% | 2
0.6 | What operation should be performed with that data i.e. Merging/Cleansing/Type casting/Data removal/Create relationship among the data/Categorise the data etc. In short what should be the business logic. |  |  | 2018-11-16 | 2018-11-19 | 2 | 0% | 2
0.7 | Pseudo logic for transformation. |  |  | 2018-11-20 | 2018-11-20 | 1
0.8 | Create the Python script for the above Transformation logic. |  |  | 2018-11-21 | 2018-11-27 | 5
0.9 | Integrate data validation |  |  | 2018-11-28 | 2018-11-28 | 1
1 | Integrate exception handling |  |  | 2018-11-29 | 2018-11-30 | 2
1 | Integrate Email configuration |  |  | 2018-12-03 | 2018-12-03 | 1
.1 | Integrate Logging |  |  | 2018-12-04 | 2018-12-05 | 2
.1 | Integrate Celery |  |  | 2018-12-06 | 2018-12-07 | 2
| Unit testing |  |  | 2018-12-07 | 2018-12-11 | 3
1 | Load the csv into Vertica |  |  |  | - |  |  | -
.1 | Load the csv into Vertica |  |  | 2018-12-12 | 2018-12-13 | 2 | 0% | 2
| Unit testing |  |  | 2018-12-14 | 2018-12-14 | 1
1 | DevOps |  |  |  | - |  |  | -
.1 | Deploy the python script on AWS |  |  | 2018-12-17 | 2018-12-19 | 3 | 0% | 3
| Integrate Autosys |  |  | 2018-12-20 | 2018-12-24 | 3
| Write Jenkins deployment script |  |  | 2018-12-25 | 2018-12-27 | 3
| Integrate Jenkins |  |  | 2018-12-28 | 2019-01-01 | 3
1 | Documentation |  |  |  | - |  |  | -
.1 | Create DDL Diagram |  |  | 2019-01-01 | 2019-01-01 | 1 | 0% | 1
.1 | Create DML Diagram |  |  | 2019-01-02 | 2019-01-02 | 1 | 0% | 1
.1 | ETL script documentation |  |  | 2019-01-03 | 2019-01-03 | 1 | 0% | 1
-
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
.1 | . . . [ Level 4 Task ] |  |  |  | - |  |  | -